## Sheet1
OVAL Testing done by Negin on 27 October logged in as Teacher One in Test Course 2 using the video HLTH 2037 Week 1
Action | Works? | Notes | Update comments 19-51 by Max Gong(max.gong@unisa.edu.au)
Creat link to OVAL from Moodle page | Yes
Link OVAL Activity from Moodle page to a particular video when video is set to 'visible' | Yes
Link OVAL Activity from Moodle page to a particular video when video is set to 'hidden' | No | When I switch role to 'student' and clink on a link that should go to a video that is 'hidden', it goes to a different video instead of not going to anything.
Change order of videos | not correct | Can change the order but it is not correct. It says HLTH 2037 video is order 1 but the nature sounds videos diplays first in the menu bar under 'home'
Add a YouTube video | Yes | But for some reason it shows up twice on the Manage Link from Moodle Page only
Make an annotation | Yes
Make an annotation that is private | Yes
Make an annotation that isvisible to all students in the course | yes
Make an annotation to nominated students | no | Although there are students registered in the course, it does not provide the list of names. Only provides the name, Teacher One
Make annotation with a tag | yes
Edit annotation with a tag | no | the original tag disappeared.
Annotation download file type displays | yes
Annotation download file, name displays | no | need to be fixed
annotation download file start time displays | yes
annotation download file tags | no | The following displays which is not easy for a teacher or student to read: | [{"id":2,"tag":"love it","created_at":"2017-10-27 11:18:16","updated_at":"2017-10-27 11:18:16","pivot":{"annotation_id":3,"tag_id":2,"created_at":"2017-10-27 11:20:37","updated_at":"2017-10-27 11:20:37"}}]
annotation download file visibility displays | yes
Quiz Tutorial page | request | Step 1. change '…set two sort of question for quiz…' to '…setup two sorts of questions for each quiz….' | changed
Quiz Tool | request | Can we change 'Q&A' to 'Short Answer Question'. Most instructors will not know what Q&A means | Change to Short Answer Questions
Quiz tool | request | Can there be an option to include an answer for the short answer question that students will see by default after submitting the quiz. It can say, this is your answer. Check to see if it matches the correct answer'. As currently, I'm not fully understanding the purpose of the Q&A question. | Add short answer instructor provided answer, it will use as reference feedback to show to student
Quiz Tutorial page | request | Step 2. change ''current quiz's questions list' to 'the current quiz's question list…' and change '…to quiz list' to '….to the quiz list'. | changed
Quiz Tutorial page | request | Remove the word 'set' under 3. Submit Quiz set to server | changed
Quiz tutorial page | request | Change title 'OVAL Quiz Set Tutorial' to 'OVAL Quiz Setup Tutorial' | changed
Quiz Tutorial page | request | At the top of the page add the following 'You can have multiple quizzes per video and multiple quiz questions per quiz. The instructions below are to setup each quiz.' | changed
Quiz Tutoria page | request | Step 3. change 'quiz set' to 'quiz setup' both times. And change 'data lost' to 'lost data'. | changed
Quiz setup add quiz at specific time code | yes
Add multipe questions to each quiz | yes
preview quiz questions | yes | But, I have to click on the 'eye' icon and typically this icon is used for 'visible' or hide' so I thought it meant I could hide the question | change icon to preview information
edit quiz | yes | But this is a bit confusing. It says 'Create new quiz @ seconds' instead of 'Edit quiz at @ seconds'. | It will show 'Edit' instead of 'create'
delete quiz question | yes | but it does not give a warning, Eg 'Are you sure you want to delete this quiz question? Cancel or Continue | add quiz question delete warning function
delete quiz | yes | But, it does not give me a warning. E.g can say 'Are you sure you want to delete this quiz and associated quiz questions? Cancel or continue. | add quiz delete warning function
edit quiz question | yes
Quiz | request | Can the instructor feedback be provided when the answer is correct as well as incorrect? | Current, we also provide feedback for correct answer
quiz | request | The quiz title is in seconds (e.g. quiz @ 190s can this be changed to minutes when over 60 seconds? | change to format XX Hours:XX minutes:XX seconds
analytics access | yes
analytics - quiz details | yes | but the titling is confusing. It says Quiz question 01: Quiz @ 7s and the next column says Quiz Question 11: Quiz @ 190s. Since the results are attempts at a quiz (not quiz question) column heading should be the name of the quiz e.g. Quiz @7s | changed column title
quiz report - quiz score | request | I am not sure how the quiz score is determined. Eg how many points per quiz question. Perhaps it should just say the percentage correct? | current, we will show percentage correct, for instance, you tried 5 times, only 1 correct, I will show score 20%
quiz report - quiz answers | no | the answers that students provide are not provided. Eg. For the Q&A questions, there is no where to see students' responses. Can a record of all students' responses be provided in the report? | add “download details” button at quiz analysis page, press this button, user could download all student record as excel files.
analytics - quiz details | request | Can it also show % of students who have attempted each quiz | add extra table to show % of students who have attempted each quiz
analtyics - dashboard % of video watched | not correct | Under Teacher One, I viewed a few seconds, but this is not required. | bug fixed
analytics - dashboard first time | not correct | I played the video a few times | bug fixed
analytics - last time video played | not correct |  | bug fixed
analytics - # of general comments viewed | not correct | It says 10 but there aren't any general comments | As I explained before, general comments are embedded in home page. I am trying to track comments event more precisely. May apply new tracking system in next version.
analytics - # of annotations viewed | not correct | I created and viewed 2 annotations | bug fixed
analytics - avg time spent viewing each annotation | not correct |  | we tested, due to tracking error, it may not reflect precisely. But the more tracking data we collect, more accurate the result will be.
analytics - was the annotations file downloaded | not correct | downloaded it at least 2 times. | bug fixed
analytics - it says 66.67% course engagement | request | what does this mean. Can there be a hover button that says how the number was calculated? E.g. Portion of all users who played the video | add tooltip pop-out window to show explaination of course engagement
analytics - under annotation column, total = 6, avg is 3 | not correct | only 3 annotations were made for this video by 2 people | bug fixed
analytics - under comments column, the unique students dashboard | not correct | avg time spent viewing each comment is wrong - says 146s. Should be changed to minutes but also there are no comments so no time spent viewing them. # of comments viewed is also wrong. Says 10. | changed to new time format XX Hours: XX minutes: XX seconds, please refer to (comment 45)
content analysis request | not correct | I requested content analysis on the video HLTH 2037 Week 1 and the message says request already exists but I never requested and I just added the video to OVAL.